## Agile Project Plan Template
Status | Category | Description | Assigned To | Start | Finish | Duration | % Complete | Predecessors
STATUS KEY
Blue | Complete
Green | In Progress
Yellow | On Hold
Red | Not Started
Green | PROJECT A |  | khalil alsulaimani | 2021-02-04 | 2022-01-31 | 258d | 65%
Blue | SPRINT 1 |  | khalil alsulaimani | 2022-01-18 | 2022-01-20 | 3d | 65%
Blue | Collect Requirmnets for login and owner screen |  | Abdulaziz | 2022-01-18 | 2022-01-20 | 3d | 73%
Blue | Task 1 | *Switch to Gantt view or Card view on the toolbar above for an interactive, visual timeline or Kanban board. | Sally J | 2022-01-18 | 2022-01-18 | 1d | 99%
Green | Task 2 |  | Bobby Marshall | 2022-01-19 | 2022-01-20 | 2d | 60% | 10
Blue | Collect Requirmnets for Manger screen |  | saher | 2022-01-18 | 2022-01-18 | 1d | 40%
Red | Task 1 |  | John Hart | *click for date
Green | Task 2 |  | *click for contact list | 2022-01-18 | 2022-01-18 | 1d | 40%
| Milestone - Set Duration to 0 |  |  | 2022-01-18 | 2022-01-18 | 0 | 20% | 14
| Collect Requirmnets for receptionest screen |  | khalil alsulaimani
Task 1
Task 2
Blue | SPRINT 2 |  | khalil alsulaimani | 2022-01-24 | 2022-01-31 | 6d | 50%
Blue | Design Login Page and Owner Screens |  | Abdulaziz | 2022-01-24 | 2022-01-31 | 6d | 50%
| Task 1 |  |  | 2022-01-24 | 2022-01-26 | 3d | 60%
| Task 2 |  |  | 2022-01-27 | 2022-01-31 | 3d | 40% | 21
Blue | Design Mannger Screens |  | saher
Task 1
Task 2
Blue | Design Receptionests Screens and create project backlog |  | khalil alsulaimani
Task 1
Task 2
Red | SPRINT 3
| Implement requriments 1-17 | login and owner main screens | Abdulaziz
Task 1
Task 2
| Implement requriments 57 - 65 | manger main screen | saher
Task 1
Task 2
| Implement requriments 99 - 109 | receptionst main screen | khalil alsulaimani
| Task 1 |  | khalil alsulaimani
Task 2
Red | SPRINT 4 |  |  | 2022-01-18 | 2022-01-20 | 3d | 65%
| Implement requriments 18-32 | edit owner operations | Abdulaziz
Task 1
Task 2
| Implement requriments 66-76 | Edit doctor operations | saher
Task 1
Task 2
| Implement requriments 110 - 118 | search patiants and book appoimnets screens | khalil alsulaimani
Task 1
Task 2
Blue | SPRINT 5 |  | khalil alsulaimani | 2022-01-18 | 2022-01-20 | 3d | 65%
| Implement requriments 32-56 | edit mannger operations | Abdulaziz
| Implement requriments 77-98 | edit receptionest operations | saher
| Configure database |  | khalil alsulaimani
Blue | SPRINT 6 |  | khalil alsulaimani | 2022-01-18 | 2022-01-20 | 3d | 65%
| testing all owner operations and screens |  | Abdulaziz
| testing all manger operations and screens |  | saher
| Test database and receptioesnt screens |  | khalil alsulaimani
| End - Set Duration to 0 |  |  | 2021-02-04 | 2021-02-04 | ~0

## Comments
Row 7 | Anyone who is the Owner of a sheet or has Editor or Admin access can add comments and attachments to any row. This keeps relevant information in context, and creates a single source for key details. Here are a few helpful resources for working with comments and attachments: https://help.smartsheet.com/articles/521892-working-with-comments https://help.smartsheet.com/articles/518408-uploading-attachments | Jillian Knoepfel | 09/29/20 5:59 PM